## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | 1 | Foundations and Prerequistes for doing the project | SHOULD HAVE | No Dependency | Charan Teja Mangali | 3- Completed
S2 | S2 | 2 | Project Understanding, Setup, project achitecture and Google sheet Integration | MUST HAVE | Python, Google Sheets API | Charan Teja Mangali | 3- Completed
S3 | S3 | 3 | Social Media Integration, Content Creation, Optimization | MUST HAVE | Social Media APIs, Python Libraries | Charan Teja Mangali | 3- Completed
S4 | S4 | 4 | Sentiment Analysis, Slack Integration and deployment | MUST HAVE | NLP Libraries, Slack API, Deployment Platform | Charan Teja Mangali | 3- Completed
Note on F1: ====== ID#AAABs4-wLUs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day 1 | Lack of clarity on project scope and AI requirements | Studied project objectives, reviewed documentation, and clarified requirements through research
S1 | Day 2 | Limited understanding of content marketing workflows | Analyzed existing content marketing strategies and studied online resources
S2 | Day 3 | Difficulty in integrating Google Sheets API | Referred official Google API documentation and implemented test integration
S2 | Day 4 | Errors during environment setup and dependency installation | Resolved issues by updating libraries and configuring the Python environment
S3 | Day 5 | Issues accessing social media APIs | Created developer accounts and configured API keys correctly
S3 | Day 6 | Performance issues in content optimization technique | Optimized Python code and tested with sample datasets
S4 | Day 7 | Inaccurate sentiment analysis result | Improved preprocessing and fine-tuned NLP library parameters
S4 | Day 8 | Slack notification Integration failure | Debugged webhook configuration and validated message payload
S4 | Day 9 | Deployment challenges on hosting platform | Adjusted configuration files and redeployed application successfully

## Sprint Backlog
L
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 64 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1 | 1 | 1 | 1 | 1.5 | 1.5
SPRINT 1 BACKLOG
1 |  | Foundations and Prerequistes for doing the project | 23rd Sep | 7th Oct | SUJEETH R K | Foundation basics of python for project | Done | 16 | Introduction | Python and jupyter installation done | Learnt Naming conventions | Python Comments and functions learnt, learnt datatypes | Jupyter installation problem solved | Practice of commenting and fuctions to be used | Learnt python flow controls | Learnt python strings | Practice of variable and datatypes using flow controls | Practice of strings methods how we use and where we use | Started implementing functions to the string | Practice of functions in jupyter | Started solving the real usage problems | Leaning to do functions as I was on leave'
[9 empty] | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28
[9 empty] | 1 | 0.45 | 1.5 | 1 | 1 | 0.5 | 0.15 | 0.5 | 1 | 1 | 1 | 1 | 1.5 | 1.5
2 |  | Project Understanding, Setup, project achitecture and Google sheet Integration | 8th Oct | 22nd Oct | SUJEETH R K | Understood Project goals,setup, and architecture structure and Google Sheet Integration implementations | Done | 13 | Practiced python basics | Learnt how to use packages | Introduction to NLP and text wrangling process | Learnt about spaCy Library usage | Understanding and practice of spaCy Library usage in NLP | Project understanding | Explained about project what i understood | Hands on experience on Virtual environment | Hugging face transformer use cases with coding | Interaction session of project understanding | Practiced the transformers uses | Revising python basics | Understanding the integrations and APIs | Done with google sheet integration
[9 empty] | Day 29 | Day 30 | Day 31 | Day 32 | Day 33 | Day 34 | Day 35 | Day 36 | Day 37 | Day 38 | Day 39 | Day 40 | Day 41 | Day 42
[9 empty] | 1 | 1.5 | 1 | 1 | 1 | 1 | 1.5 | 1.5 | 1 | 1.5 | 1.5 | 1 | 1.5 | 1.5
3 |  | Social Media Integration, Content Creation, Optimization | 23rd Oct | 6th nov | SUJEETH R K | Pratical implementation of the Content generation and API integrations with code | Done | 17.5 | API integration with twitter | Worked on API integration of twitter | Working with Meta API | Tried linked in API integration | Interactive session with sir | Practicing the APi integration code | Introduction to mock data generation | Use LLM and accessing groq API | Practical on gsheet_connector | Fundamentals of Gen AI and LLM | Worked on gsheet_connector with different platforms | Learnt about LLM | Content generation practical usage | created different templates for content generation
[9 empty] | Day 43 | Day 44 | Day 45 | Day 46 | Day 47 | Day 48 | Day 49 | Day 50 | Day 51 | Day 52 | Day 53 | Day 54 | Day 55 | Day 56
[9 empty] | 1 | 0.5 | 1 | 2 | 1 | 1 | 1 | 1.5 | 1 | 1.45 | 2 | 1.5 | 0.45 | 1.5
4 |  | Sentiment Analysis, Slack Integration and deployment | 6th Nov | 20th Nov | SUJEETH R K | Sentiment Analysis, Slack Integration and deployment | Done | 17.5 | Got the fundamentals of API | Theory of API concept | Worked on GROQ API | Assigment on template suggestions | Interactive session | Concept on content optimization | Studied sentiment analysis | Slack integration usage | A/B testing understanding | A/B testing continuous usage in real world | Practice of model use case | Workflow of our project discussed | Presentation preparation | Done with mock presentation
Note on D2: ====== ID#AAABs4-wLUI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABs4-wLVM Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABs4-wLUM Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABs4-wLUY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABs4-wLU8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABs4-wLUw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABs4-wLU0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABs4-wLVA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABs4-wLUU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABs4-wLUc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABs4-wLUg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABs4-wLUk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABs4-wLVE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABs4-wLUo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABs4-wLVI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABs4-wLUQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABs4-wLU4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work
Note on J7: ====== ID#AAABs4-wLUY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K7: ====== ID#AAABs4-wLU8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L7: ====== ID#AAABs4-wLUw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M7: ====== ID#AAABs4-wLU0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N7: ====== ID#AAABs4-wLVA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O7: ====== ID#AAABs4-wLUU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P7: ====== ID#AAABs4-wLUc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q7: ====== ID#AAABs4-wLUg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R7: ====== ID#AAABs4-wLUk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S7: ====== ID#AAABs4-wLVE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T7: ====== ID#AAABs4-wLUo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U7: ====== ID#AAABs4-wLVI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V7: ====== ID#AAABs4-wLUQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W7: ====== ID#AAABs4-wLU4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work
Note on J10: ====== ID#AAABs4-wLUY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K10: ====== ID#AAABs4-wLU8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L10: ====== ID#AAABs4-wLUw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M10: ====== ID#AAABs4-wLU0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N10: ====== ID#AAABs4-wLVA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O10: ====== ID#AAABs4-wLUU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P10: ====== ID#AAABs4-wLUc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q10: ====== ID#AAABs4-wLUg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R10: ====== ID#AAABs4-wLUk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S10: ====== ID#AAABs4-wLVE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T10: ====== ID#AAABs4-wLUo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U10: ====== ID#AAABs4-wLVI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V10: ====== ID#AAABs4-wLUQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W10: ====== ID#AAABs4-wLU4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work
Note on J13: ====== ID#AAABs4-wLUY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K13: ====== ID#AAABs4-wLU8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L13: ====== ID#AAABs4-wLUw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M13: ====== ID#AAABs4-wLU0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N13: ====== ID#AAABs4-wLVA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O13: ====== ID#AAABs4-wLUU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P13: ====== ID#AAABs4-wLUc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q13: ====== ID#AAABs4-wLUg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R13: ====== ID#AAABs4-wLUk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S13: ====== ID#AAABs4-wLVE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T13: ====== ID#AAABs4-wLUo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U13: ====== ID#AAABs4-wLVI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V13: ====== ID#AAABs4-wLUQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W13: ====== ID#AAABs4-wLU4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2025-09-12 | 2025-09-30 | SUJEETH R K | Writing daily running notes | Skipping basics | Python practice | Strengthened Python fundamentals
2 | S2 | 2025-10-01 | 2025-10-09 | SUJEETH R K | Modular coding | Writing long scripts | Function-based coding | Improved code readability
3 | S3 | 2025-10-10 | 2025-10-16 | SUJEETH R K | NLP preprocessing | Ignoring text cleaning | Using libraries | Better text handling
4 | S4 | 2025-10-21 | 2025-10-24 | SUJEETH R K | API-based integration | Manual data handling | Google Sheets usage | Automated data flow
5 | S5 | 2025-10-29 | 2025-10-31 | SUJEETH R K | Milestone tracking | Delayed testing | Mock data testing | Validated milestone-1
6 | S6 | 2025-11-01 | 2025-11-07 | SUJEETH R K | LLM exploration | Using defaults blindly | Model experimentation | Improved content generation
7 | S7 | 2025-11-10 | 2025-11-24 | SUJEETH R K | Optimization & documentation | Last-minute fixes | Regular reviews | Final project submission